# Community Development Alliance Action Plan Year 1 Progress Update 24-5

| Table 1:Community Priority 1: Increase Understanding of Community Empowerment |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Action | *WD Community planning outcomes | Lead | timescale | National Community Development Outcome | Method/ Measure of success | Progress |
| Refresh Community Empowerment Communications Plan and implement findings of Communications Plan Consultation | Promoting Active Citizenship Delivering Community Led approaches | WD Communities Team | YR1 | Communities are confident resilient and optimistic for the future. Communities manage links within communities and to other communities and networks. | information sessions / consultation and findings report. | Amber: Third sector CE awareness survey undertaken. Mixed levels of awareness identified (WDCVS) Planned Action 25/6: - Community Assets presentation by DTAS at TSLC (June 2025) - WDCVS website refresh (July 2025) - Inputs to TSLF meetings (Sept/Dec/March 2025) - Celebrating Community WD events. |
| Hold Community Empowerment Drop ins and Surgeries in Communities | Promoting Active Citizenship Delivering Community Led approaches | WD Communities Team WDCVS | YR 1 | Communities are confident resilient and optimistic for the future. Communities manage links within communities and to other communities and networks. | Tracking of enquiries/ conversations. Community case studies. | Green: 156 organisation surgeries delivered (WDCVS) Communities Team- Range of Community Surgeries and Drop-ins in community facilities held discussing and recording CE barriers with local people. (Communities Team) Support for Community Soup events hosted by communities (Communities Team) Planned Action 25/6: - Maintain weekly surgery delivery (ongoing) - On Your Doorstep outreach programme (Aug-Oct 25) (WDCVS) |
| Review and implement improvements to raise awareness of the community empowerment strategy/agenda | Promoting Active Citizenship Delivering Community Led approaches | WD Communities Team | YR 1 | Communities are confident resilient and optimistic for the future. Communities manage links within communities and to other communities and networks. | Events hosted by CPWD and engaging local groups in active participation Accessible information finalised and uploaded to website | Amber: Increased CE awareness inputs delivered across a range of CPWD events including Family Prosperity Network development Planned Action 25/6: - In-person CES refresh session (Aug/Sept 25) |
| Continue to promote the use of the Place Standard in communities across WD | Delivering Community Led approaches | WDC Planning WD Communities Team | YR 1 | Communities are confident resilient and optimistic for the future. Community members identify their capacities, learning and skills, enhance them and apply them to their own issues and needs | Qualitative data on approaches being taken across WD (e.g. 20-minute neighbourhood, Shaping Places for Wellbeing) | Amber: “Tell Us About Your Place’ session conducted to inform Local development Plan using the Place Standard (Communities Team) |

| Table 2: Community Priority 2: Increase Confidence for Community Empowerment |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Action | *WD Community planning outcomes | Lead | timescale | National Community Development Outcome | Method/ Measure of success | progress |
| Continue to support communities with Locality Planning. | Promoting Active Citizenship Delivering Community Led approaches. | WD Communities WD Community Council Forum | YR 1 | Communities are confident resilient and optimistic for the future. Community members identify their capacities, learning and skills, enhance them and apply them to their own issues and needs. | Number of opportunities created for communities to engage with community and locality planning. | Green: 3 Locality Plans completed for Clydebank Waterfront, Dumbarton and Leven. Place Plans are being developed in 3 locations- Old Kilpatrick, Alexandria and Dumbarton West (supported by CORRA). (Communities Team) |
| Develop and deliver future phases of Participatory Budgeting and Mainstreaming. | Promoting Active Citizenship Delivering Community Led approaches | WD Communities Team | YR 1 | Community members perspectives are broadened through new and diverse experiences and connections. | PB phases and value delivered, evaluation of phase. Scottish Government Report on Contribution to 1% Community Choices target. | Amber: The final Community Budgeting event took place February to March 2025. This provided small grant funding for communities addressing food insecurity at a local level. Future delivery opportunities unclear at present. |

| Table 3: Community Priority 3: Set Standards for how we Work and Behave |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Action | *WD Community planning outcomes | Lead | timescale | National Community Development Outcome | Method/ Measure of success | progress |
| Awareness and training on the National Standards for Community Engagement for the Council, Community Planning partners and communities. | Promoting Active Citizenship | WD Communities WDCVS | YR 1 | Community members identify their capacities, learning and skills, enhance them and apply them to their own issues and needs. | Increase in number of registrations to CLD Standards Council. National Standards for Community Engagement are adopted for Community engagement and service delivery | Amber: Presentation from CLDSC at June 24 TSLC (WDCVS) Inclusion of encouragement to join as part of WDCVS 6-monthly relationship visits to organisations. Planned Action 25/6: - CLDSC representation at TSLC Jun 25 - Target of 25% of TSOs to apply for membership (25/6) - Pilot of ‘Volunteer Ready’ joint induction programme across TSOs |

| Table 4: Community Priority 4: Ensure Clarity of Roles for Effective Collaboration |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Action | *WD Community planning outcomes | Lead | timescale | National Community Development Outcome | Method/ Measure of success | progress |
| Ensure clarity of roles and effective collaboration amongst Councillors, Council Officers, CPP partners, volunteers and Communities. | Promoting Active Citizenship | WD Communities | YR 1 | Communities manage links within communities and to other communities and networks. | Clear online information about everyone’s roles. Accessible information finalised and uploaded to website. | Amber: Information sessions provided to Elected Members and senior officers of WDC. (Communities Team & WD Leisure Trust) |

| Table 5: Community Priority 5: Develop Skills for Community Empowerment |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Action | *WD Community planning outcomes | Lead | timescale | National Community Development Outcome | Method/ Measure of success | progress |
| Offer capacity building and development support to emerging and established community groups/ organisations. | Promoting Active Citizenship Delivering Community Led approaches | WD Communities | Yr1 | Community members identify their capacities, learning and skills, enhance them and apply them to their own issues and needs. | No of development opportunities offered. No of people/ groups engaged in Community activity. | Green: 14 New groups supported 92 Proactive funding approaches 15 Aspire Healthchecks 79 Volunteer Development surgeries 207 new volunteer starts (WDCVS) |

| Table 6: Community Priority 6: Ensure Sufficient Resources, Facilities and Support |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Action | *WD Community planning outcomes | Lead | timescale | National Community Development Outcome | Method/ Measure of success | progress |
| Access to information, support and advice on community empowerment for local communities. | Promoting Active Citizenship Supporting Local Regeneration and Environmental Sustainability | WD Assets WD Communities | YR1 | Communities manage links within communities and to other communities and networks. | Published clear policy and guidance on - Asset Transfer - Participation Requests - Asset Register - Common Good Register and other aspects of community empowerment legislation. | Amber: Third sector CE awareness survey undertaken. Mixed levels of awareness identified (WDCVS) Intensive support delivered to 5 TSOs considering asset management/transfer 2 supported to business plan/app stage (WDCVS) 2 community management bids supported via local Community Sports Hubs (WD Leisure Trust) Planned Action 25/6: - WDCVS website refresh to clarify processes (July 2025) - Engage with WDC Asset Team to review/refresh materials (Sept 2025) - Increased role of capacity building support within Assets Team |
| Ensuring good quality, affordable and accessible spaces for community activities. | Promoting Active Citizenship Delivering Community Led approaches Supporting Local Regeneration and Environmental Sustainability | WD Communities WD Greenspace WD Leisure Trust | YR1 | Community members identify their capacities, learning and skills, enhance them and apply them to their own issues and needs. Communities manage links within communities and to other communities and networks. | Continuation of investment in Participatory Budgeting, co-producing improvements With local communities. No of community spaces supported through PB process. | Amber: Support offered for groups using WDLT community facilities to enhance their governance and/or seek additional funding in order to meet additional costs and charging conditions. (Communities Team) |